## Start Here
Clinic Appointment Scheduling Upgrade – PM Workbook
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Organisation | Riverbend Community Hospital (fictional) – 200-bed provider with 6 outpatient clinics
Sponsor | David Mensah, Chief Operating Officer
Project Manager | Sola Debanjo, PMP
Approach | Hybrid (Waterfall governance + Agile configuration sprints)
Duration (weeks) | 21
Budget (assumed) | CAD $850,000 (assumed; includes 10% contingency)
How to use this workbook
• Blue text on a yellow background = an input you can change (e.g., project start date, status week, actuals).
• Black text = formulas. They recalculate automatically when inputs change.
• Gantt: change the project start date or a task's start week/duration and the bars and dates move.
• RAID: Score = Probability × Impact; colour turns red at 15+, amber at 8–14.
• The schedule is also provided as a Microsoft Project XML file (opens in MS Project or the free ProjectLibre).

## Dashboard
Clinic Scheduling Upgrade – Week 12 status
Simulated data – built in Excel
Measure | Actual | Plan / target | % / variance
Budget spent (CAD) | 402000 | 850000 | 47.29%
Schedule elapsed (weeks) | 12 | 21 | 57.14%
System test cases passed | 142 | 160 | 88.75%
Critical defects open | 0 | 0 | 0
Super-users trained | 12 | 12 | 100%

## Gantt
Gantt Schedule
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
| Start date (Week 1): | 2026-01-05
ID | Phase | Work package / milestone | Owner | Start wk | Duration (wks) | End wk | Start date | Finish date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Initiation | Charter, stakeholder analysis, governance setup | PM | 1 | 2 | 2 | 2026-01-05 | 2026-01-16 | bar: 1 to 2
2 | Requirements | Clinic workflow mapping & requirements | Clinical Lead | 2 | 2 | 3 | 2026-01-12 | 2026-01-23 | bar: 2 to 3
3 | Requirements | Privacy impact assessment | Privacy Officer | 3 | 4 | 6 | 2026-01-19 | 2026-02-13 | bar: 3 to 6
4 | Design & Configuration | Configuration design (templates, rules) | Vendor | 4 | 3 | 6 | 2026-01-26 | 2026-02-13 | bar: 4 to 6
5 | Design & Configuration | Configuration sprints 1–3 | Vendor | 7 | 6 | 12 | 2026-02-16 | 2026-03-27 | bar: 7 to 12
6 | Design & Configuration | Integration build (interface engine) | IT Lead | 7 | 4 | 10 | 2026-02-16 | 2026-03-13 | bar: 7 to 10
7 | Data Migration | Migration mapping & trial load | IT Lead | 9 | 4 | 12 | 2026-03-02 | 2026-03-27 | bar: 9 to 12
8 | Testing | System & integration testing | IT Lead | 11 | 3 | 13 | 2026-03-16 | 2026-04-03 | bar: 11 to 13
9 | Testing | User acceptance testing (UAT) | Clinical Lead | 14 | 3 | 16 | 2026-04-06 | 2026-04-24 | bar: 14 to 16
10 | Readiness | Training (super-users then all staff) | Booking Lead | 13 | 5 | 17 | 2026-03-30 | 2026-05-01 | bar: 13 to 17
11 | Readiness | Cutover rehearsal & go-live checklist | PM | 16 | 2 | 17 | 2026-04-20 | 2026-05-01 | bar: 16 to 17
12 | Deployment | Weekend cutover & go-live | PM | 18 | 1 | 18 | 2026-05-04 | 2026-05-08 | bar: 18
13 | Hypercare & Closure | Hypercare (4 weeks incl. go-live week) | IT Lead | 18 | 4 | 21 | 2026-05-04 | 2026-05-29 | bar: 18 to 21
14 | Hypercare & Closure | Benefits baseline handover & closure report | PM | 20 | 2 | 21 | 2026-05-18 | 2026-05-29 | bar: 20 to 21
15 | Milestone | Charter approved |  | 1 | 0 | 1 | 2026-01-05 | 2026-01-05 | bar: 1
16 | Milestone | Requirements signed off |  | 3 | 0 | 3 | 2026-01-19 | 2026-01-19 | bar: 3
17 | Milestone | Configuration design approved |  | 6 | 0 | 6 | 2026-02-09 | 2026-02-09 | bar: 6
18 | Milestone | Integration build complete |  | 10 | 0 | 10 | 2026-03-09 | 2026-03-09 | bar: 10
19 | Milestone | Data migration trial reconciled |  | 12 | 0 | 12 | 2026-03-23 | 2026-03-23 | bar: 12
20 | Milestone | UAT sign-off |  | 16 | 0 | 16 | 2026-04-20 | 2026-04-20 | bar: 16
21 | Milestone | Go / no-go decision |  | 17 | 0 | 17 | 2026-04-27 | 2026-04-27 | bar: 17
22 | Milestone | Go-live (all clinics) |  | 18 | 0 | 18 | 2026-05-04 | 2026-05-04 | bar: 18
23 | Milestone | Hypercare exit & closure |  | 21 | 0 | 21 | 2026-05-25 | 2026-05-25 | bar: 21

## Stakeholders
Stakeholders
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Stakeholder | Role | Primary concern | Influence | Interest | Engagement approach
David Mensah | Executive Sponsor (COO) | Outcome, patient safety and budget | High | High | Monthly steering; weekly 1-page update; decision requests with options
Mariam Bello | Clinical / Service Lead (Outpatient Services Manager) | Operational impact and adoption | High | High | Weekly working group; co-designs clinic templates; signs off UAT
Fatima Sule | Technology Lead (IT Applications Manager) | Integration, security and delivery capacity | High | High | Weekly working group; owns technical design and integration
Michael Adekunle | Operations / Frontline Lead (Booking Office Supervisor) | Workflow disruption and usability | Medium | High | Super-user network lead; early demos; training schedule
Vendor Implementation Lead | Supplier | Contract scope and payment milestones | Medium | High | Weekly vendor checkpoint; milestone evidence reviews
Privacy Officer | Compliance | Patient data protection, access control | High | Medium | Privacy impact assessment; review of reminder content
Clinic physicians | End users (clinical) | Clinic templates, session lengths | Medium | Medium | Clinic huddles; template review sessions
Booking & reception staff | End users | Ease of use, workload during cutover | Low | High | Super-users, hands-on training, floor-walkers at go-live
Patients / Patient Advisory Council | Service users | Clear reminders, no lost appointments | Low | Medium | Reminder wording tested with council; patient notices

## RACI
RACI
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Activity / deliverable | Sponsor | PM (Sola) | Clinical Lead | IT Lead | Booking Lead | Vendor | Privacy Officer | A count (must be 1)
Project charter | A | R | C | C | I | I | I | 1
Requirements & clinic templates | I | A | R | C | R | C | I | 1
Integration build & testing | I | A | C | R | I | R | I | 1
Privacy impact assessment | I | A | C | C | I | C | R | 1
Data migration & reconciliation | I | A | C | R | R | R | I | 1
Training | I | A | C | I | R | R | I | 1
UAT sign-off | I | R | A | C | R | C | I | 1
Go / no-go decision | A | R | C | C | C | C | C | 1
Hypercare & issue resolution | I | A | C | R | R | R | I | 1
R = Responsible · A = Accountable · C = Consulted · I = Informed. Check column: each row must have exactly one A.

## RAID Log
RAID Log
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Type | ID | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Response / action | Status | Review week
Risk | R-01 | Vendor misses integration milestone, delaying system testing | 3 | 5 | 15 | IT Lead | Weekly evidence-based checkpoints (test results, not verbal updates); contractual milestone tied to payment | Occurred → see I-01 | 10
Risk | R-02 | Booking staff resist new workflows, slowing adoption | 3 | 4 | 12 | Booking Lead | Super-user network, early demos, floor-walkers in go-live week | Open | 12
Risk | R-03 | Migrated appointments lost or duplicated | 2 | 5 | 10 | IT Lead | Two trial loads with 100% reconciliation; freeze window before cutover | Open | 12
Risk | R-04 | Reminder messages expose patient information | 2 | 5 | 10 | Privacy Officer | Minimum-data message template approved by Privacy Officer | Closed | 6
Risk | R-05 | Clinicians unavailable for UAT | 3 | 3 | 9 | Clinical Lead | UAT slots booked in Week 6; clinic sessions backfilled | Open | 13
Assumption | A-01 | Legacy system remains read-only for 6 months |  |  |  | IT Lead | Confirmed with IT Director | Validated | 4
Issue | I-01 | Vendor missed integration-complete milestone (Week 10); proposed 1-week recovery without evidence | 5 | 4 | 20 | PM | Decision D-03 / change request CR-03 (see decision log) | Resolved | 12
Dependency | D-01 | Interface engine team capacity (2 days/week from Week 7) |  |  |  | IT Lead | Agreed in writing with integration manager; tracked weekly | Open | 11
Dependency | D-02 | Privacy impact assessment approval before reminder go-live |  |  |  | Privacy Officer | Submitted Week 4; approved Week 6 | Closed | 6
Open risks scored 15+: |  | 0

## Comms Plan
Comms Plan
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Audience | Information | Format / channel | Frequency | Owner | Escalation route
Steering Committee | Status, RAG, budget, decisions needed | Steering meeting + 1-page report | Monthly | PM | Sponsor
Executive Sponsor | Progress, top risks, decisions | 1-page email update + 15-min call | Weekly | PM | Steering Committee
Project working group | Plan, RAID, actions | Teams meeting + RAID log | Weekly | PM | Sponsor
Vendor | Milestone evidence, defects | Checkpoint call + defect tracker | Weekly | IT Lead | PM → Sponsor
Clinic managers & physicians | What changes, when, what they need to do | Clinic huddle slot + newsletter | Bi-weekly | Clinical Lead | PM
Booking & reception staff | Training dates, go-live support | Team briefings, quick-reference guides | Bi-weekly, daily in go-live week | Booking Lead | PM
Patients | New reminder messages | Clinic posters, website notice | Once before go-live | Clinical Lead | —

## Budget
Budget
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Cost category | Amount (CAD) | Notes
Vendor licences & implementation services | 410000 | Fixed-price contract
Internal IT & interface engine effort | 150000 | Backfill for analysts
SMS/email reminder service (Year 1) | 45000 | Per-message pricing
Training & backfill for booking staff | 90000 | 2 sessions per person
Project management & change management | 77000
Contingency (10%) | 78000 | Released by sponsor only
Total | 850000
Contingency as % of total | 9.176%

## Scope Backlog
Scope Backlog
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
ID | User story | Priority (MoSCoW) | Acceptance criteria | Release | Status
B-01 | As a booking clerk, I can book an appointment from a clinic template so sessions are not double-booked | Must | System blocks overlapping bookings for same clinician/room; tested on all 6 clinic templates | Go-live | Done
B-02 | As a patient, I receive a reminder 48 h before my appointment | Must | SMS or email sent for 100% of booked appointments in test; message contains no clinical details | Go-live | Done
B-03 | As a patient, I can reply to cancel so the slot can be reused | Should | Reply 'C' cancels and frees slot within 5 min; booking office notified | Go-live | Done
B-04 | As a clinic manager, I see daily utilisation and no-shows by clinic | Must | Report available by 08:00 daily; figures match source within 1% | Go-live | Done
B-05 | As a booking clerk, patient demographics load from the patient administration system | Must | Demographics returned in under 3 s; no manual re-keying | Go-live | Done
B-06 | As IT, all access is role-based and audited | Must | Access review completed; audit log captures view/edit events | Go-live | Done
B-07 | As a booking clerk, I can manage a wait list and offer cancelled slots | Should | Wait-list patients offered freed slot automatically | Release 1.1 | Backlog
B-08 | As a patient, I can book online | Could | — | Phase 2 | Deferred
B-09 | Interpreter booking flag | Should | Flag visible on appointment and in daily list | Release 1.1 | Backlog
B-10 | Multi-language reminders | Won't (this phase) | — | Phase 2 | Deferred