## Start Here
Customer Churn Reduction Project – PM Workbook
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Organisation | ClearWave Telecom (fictional) – regional home-internet and SME broadband provider, ~180,000 subscribers
Sponsor | Daniel Adebayo, Chief Commercial Officer
Project Manager | Sola Debanjo, PMP
Approach | Waterfall (stage-gated)
Duration (weeks) | 43
Budget (assumed) | CAD $1.2M (assumed; includes 10% contingency)
How to use this workbook
• Blue text on a yellow background = an input you can change (e.g., project start date, status week, actuals).
• Black text = formulas. They recalculate automatically when inputs change.
• Gantt: change the project start date or a task's start week/duration and the bars and dates move.
• RAID: Score = Probability × Impact; colour turns red at 15+, amber at 8–14.
• The schedule is also provided as a Microsoft Project XML file (opens in MS Project or the free ProjectLibre).

## Dashboard
Churn Reduction – benefits KPIs after go-live
Simulated data – built in Excel
KPI | Baseline | Month 1 | Month 2 | Month 3 | Target | Better if | Status vs target (Month 3)
Monthly churn rate | 2.4% | 2.3% | 2.2% | 2.1% | 1.9% | lower | Not yet – 0.2% to go
Save rate (save desk) |  | 28% | 31% | 33% | 35% | higher | Not yet – 2.0% to go
Offer approval within 24 h | 40% | 88% | 93% | 96% | 95% | higher | Met
Repeat complaints within 30 days | 22% | 21% | 19% | 18% | 15% | lower | Not yet – 3.0% to go
Target line values (used by the charts below)
Monthly churn rate target | 1.9% | 1.9% | 1.9% | 1.9%
Save rate (save desk) target | 35% | 35% | 35% | 35%
Offer approval within 24 h target | 95% | 95% | 95% | 95%
Repeat complaints within 30 days target | 15% | 15% | 15% | 15%
Period labels | Baseline | Month 1 | Month 2 | Month 3

## Gantt
Gantt Schedule
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
| Start date (Week 1): | 2026-01-05
ID | Phase | Work package / milestone | Owner | Start wk | Duration (wks) | End wk | Start date | Finish date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
1 | Initiation | Charter, business case validation, governance | PM | 1 | 3 | 3 | 2026-01-05 | 2026-01-23 | bar: 1 to 3
2 | Requirements & Analysis | Churn root-cause analysis (24 months of data) | BI/CRM Lead | 4 | 4 | 7 | 2026-01-26 | 2026-02-20 | bar: 4 to 7
3 | Requirements & Analysis | Current-state process mapping | Business Owner | 4 | 3 | 6 | 2026-01-26 | 2026-02-13 | bar: 4 to 6
4 | Requirements & Analysis | Requirements & scoring rules sign-off | Business Owner | 7 | 4 | 10 | 2026-02-16 | 2026-03-13 | bar: 7 to 10
5 | Design | Data mart & report design | BI/CRM Lead | 11 | 6 | 16 | 2026-03-16 | 2026-04-24 | bar: 11 to 16
6 | Design | Future-state process & save-desk model | Contact Centre | 11 | 5 | 15 | 2026-03-16 | 2026-04-17 | bar: 11 to 15
7 | Design | Offer matrix & finance approval | Finance | 13 | 4 | 16 | 2026-03-30 | 2026-04-24 | bar: 13 to 16
8 | Build | Data integration (billing, CRM, network tickets) | BI/CRM Lead | 17 | 10 | 26 | 2026-04-27 | 2026-07-03 | bar: 17 to 26
9 | Build | CRM offer-approval workflow | BI/CRM Lead | 19 | 8 | 26 | 2026-05-11 | 2026-07-03 | bar: 19 to 26
10 | Build | Save-desk recruitment, scripts & training | Contact Centre | 22 | 8 | 29 | 2026-06-01 | 2026-07-24 | bar: 22 to 29
11 | Testing | System & data-quality testing | BI/CRM Lead | 29 | 3 | 31 | 2026-07-20 | 2026-08-07 | bar: 29 to 31
12 | Testing | User acceptance testing | Business Owner | 32 | 3 | 34 | 2026-08-10 | 2026-08-28 | bar: 32 to 34
13 | Deployment | Go-live & stabilisation | PM | 37 | 2 | 38 | 2026-09-14 | 2026-09-25 | bar: 37 to 38
14 | Benefits & Closure | Benefits tracking & closure pack | PM | 39 | 5 | 43 | 2026-09-28 | 2026-10-30 | bar: 39 to 43
15 | Milestone | Gate 1 – Charter approved |  | 3 | 0 | 3 | 2026-01-19 | 2026-01-19 | bar: 3
16 | Milestone | Gate 2 – Requirements signed off |  | 10 | 0 | 10 | 2026-03-09 | 2026-03-09 | bar: 10
17 | Milestone | Gate 3 – Design approved |  | 16 | 0 | 16 | 2026-04-20 | 2026-04-20 | bar: 16
18 | Milestone | Build complete |  | 28 | 0 | 28 | 2026-07-13 | 2026-07-13 | bar: 28
19 | Milestone | Gate 4 – UAT sign-off |  | 34 | 0 | 34 | 2026-08-24 | 2026-08-24 | bar: 34
20 | Milestone | Go / no-go decision |  | 35 | 0 | 35 | 2026-08-31 | 2026-08-31 | bar: 35
21 | Milestone | Go-live |  | 37 | 0 | 37 | 2026-09-14 | 2026-09-14 | bar: 37
22 | Milestone | Benefits review & closure |  | 43 | 0 | 43 | 2026-10-26 | 2026-10-26 | bar: 43

## Stakeholders
Stakeholders
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Stakeholder | Role | Primary concern | Influence | Interest | Engagement approach
Daniel Adebayo | Executive Sponsor (CCO) | Business outcome and timeline | High | High | Monthly steering; gate approvals; weekly update
Ngozi Ibe | Product / Business Owner (Head of Customer Retention) | Scope and user value | High | High | Weekly; owns requirements and offer matrix
Emeka Umeh | Technology / Delivery Lead (BI & CRM Manager) | Feasibility and team capacity | High | High | Weekly; owns data mart and CRM build
Ruth Asante | Operations / Customer Lead (Contact Centre Manager) | Adoption and service continuity | High | High | Weekly; owns save desk and training
Field Sales Lead | Sales | Commission impact, SME accounts | Medium | High | Bi-weekly; SME retention input
Finance Business Partner | Finance | Cost of retention offers | High | Medium | Offer budget approval at Gate 3
Network Operations Manager | Dependency owner | Maintenance windows, outage data | Medium | Low | Monthly; data feed agreement
Legal & Privacy | Compliance | Consent for outbound contact, data use | High | Low | Review at design and before win-back launch
Contact centre agents | End users | Workload, clear scripts, targets | Low | High | Agent focus groups, training, feedback loop

## RACI
RACI
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Activity / deliverable | Sponsor | PM (Sola) | Business Owner | BI/CRM Lead | Contact Centre | Finance | Legal | A count (must be 1)
Charter & gate approvals | A | R | C | C | C | I | I | 1
Current/future-state process map | I | A | R | C | R | I | I | 1
Churn-risk scoring rules | I | C | A | R | C | I | C | 1
Data mart & risk report build | I | C | C | A | I | I | I | 1
Offer matrix & approval workflow | C | R | A | R | C | C | I | 1
Save-desk set-up & training | I | C | C | I | A | I | I | 1
Win-back campaign consent review | I | R | C | I | I | I | A | 1
UAT sign-off | I | R | A | R | R | I | I | 1
Go / no-go | A | R | C | C | C | I | C | 1
Benefits / KPI dashboard | I | A | C | R | C | C | I | 1
R = Responsible · A = Accountable · C = Consulted · I = Informed. Check column: each row must have exactly one A.

## RAID Log
RAID Log
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Type | ID | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Response / action | Status | Review week
Risk | R-01 | Billing and CRM account IDs don't match, so risk scores attach to the wrong customer | 3 | 5 | 15 | BI/CRM Lead | Data-quality rules + reconciliation in system test | Occurred → I-02 | 33
Risk | R-02 | Network maintenance windows delay data-feed testing | 3 | 4 | 12 | PM | Book windows 6 weeks ahead; use extract file as fallback | Open | 26
Risk | R-03 | Agents see save desk as extra workload; low adoption | 3 | 4 | 12 | Contact Centre | Agent focus groups, clear targets, recognition scheme | Open | 30
Risk | R-04 | Retention offers erode revenue more than churn saves | 2 | 4 | 8 | Finance | Offer matrix with margin floor; Finance monthly review | Open | 16
Risk | R-05 | Win-back contact breaches consent rules | 2 | 5 | 10 | Legal | Legal review; consent flag filter on campaign list | Closed | 34
Assumption | A-01 | 24 months of history available and usable |  |  |  | BI/CRM Lead | Validated in Week 5 (21 months usable) | Validated with gap | 6
Issue | I-01 | Stakeholders asked to add SME 'contract renewal' alerts after seeing first report | 4 | 3 | 12 | PM | Assessed via CR-02; approved with 1-week impact | Resolved | 20
Issue | I-02 | UAT found duplicate SME account IDs causing wrong-customer risk scores (2 weeks before go-live) | 5 | 5 | 25 | PM | Phased go-live decision – see decision log D-05 | Resolved | 37
Dependency | D-01 | Network ticket data feed (Network Operations) |  |  |  | PM | Data-sharing agreement signed Week 12 | Open | 28
Dependency | D-02 | Finance approval of offer budget before Gate 3 |  |  |  | Finance | Approved Week 15 | Closed | 16
Open risks scored 15+: |  | 0

## Comms Plan
Comms Plan
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Audience | Information | Format / channel | Frequency | Owner | Escalation route
Steering Committee | Gate readiness, RAG, budget, decisions | Steering pack (5 slides) | Monthly + each gate | PM | Sponsor
Executive Sponsor | Status, risks, decisions | 1-page status report | Weekly | PM | Steering Committee
Workstream leads | Plan, RAID, dependencies | Delivery meeting + RAID log | Weekly | PM | Sponsor
Contact centre agents | Save-desk changes, scripts, training | Team huddles, intranet FAQ | Bi-weekly; daily at launch | Contact Centre Manager | PM
Field sales | SME retention process | Sales meeting slot | Monthly | Field Sales Lead | Business Owner
Finance | Offer spend vs saves | Benefits dashboard extract | Monthly after go-live | BI/CRM Lead | Sponsor

## Budget
Budget
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Cost category | Amount (CAD) | Notes
Data integration & BI development | 420000 | Data engineers, BI developer
CRM workflow configuration | 180000 | CRM partner
Save-desk set-up & training | 170000 | Scripts, coaching, backfill
Process redesign & change management | 120000
Project management & QA | 200000
Contingency (10%) | 110000
Total | 1200000
Contingency as % of total | 9.167%

## KPI Definitions
KPI Definitions
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
KPI | Baseline | Target | Measurement method | Owner | Cadence
Monthly churn rate | 2.4% | 1.9% | Disconnects ÷ active subscribers at month start | Head of Retention | Monthly
Save rate (save desk) | n/a | 35% | Customers retained ÷ cancellation requests handled | Contact Centre Manager | Weekly
Offer approval within 24 h | ~40% | 95% | CRM workflow timestamps | Business Owner | Weekly
Repeat complaints within 30 days | 22% | 15% | Complaint records, same account, 30 days | Contact Centre Manager | Monthly
Retention offer cost per save | n/a | ≤ $60 | Offer cost ÷ saves | Finance | Monthly