## Start Here
HR Helpdesk & Case Management System (IT Service Management) – PM Workbook
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Organisation | Prairie Shield Financial Group (fictional) – regional banking group, ~2,400 employees
Sponsor | James Okoro, Chief Human Resources Officer
Project Manager | Sola Debanjo, PMP
Approach | Agile (Scrum – 2-week sprints)
Duration (weeks) | 15
Budget (assumed) | CAD $180,000 (assumed; includes 10% contingency)
How to use this workbook
• Blue text on a yellow background = an input you can change (e.g., project start date, status week, actuals).
• Black text = formulas. They recalculate automatically when inputs change.
• Gantt: change the project start date or a task's start week/duration and the bars and dates move.
• RAID: Score = Probability × Impact; colour turns red at 15+, amber at 8–14.
• The schedule is also provided as a Microsoft Project XML file (opens in MS Project or the free ProjectLibre).

## Dashboard
HR Helpdesk – sprint velocity and pilot service levels
Simulated data – built in Excel
Sprint | Story points completed
Sprint 1 | 10
Sprint 2 | 13
Sprint 3 | 6
Sprint 4 | 15
Sprint 5 | 2
Total delivered | 46
Backlog points in scope (excl. deferred) | 46
Average velocity (Sprints 1–4) | 11
Pilot service metric | Value
Tickets logged (3 weeks) | 312
Tickets with first response ≤ 1 business day | 284
First-response SLA % | 91.03%
SLA target | 90%
SLA status | Met

## Gantt
Gantt Schedule
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
| Start date (Week 1): | 2026-01-05
ID | Phase | Work package / milestone | Owner | Start wk | Duration (wks) | End wk | Start date | Finish date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Sprint 0 | Charter, discovery interviews, backlog & design | PM | 1 | 2 | 2 | 2026-01-05 | 2026-01-16 | bar: 1 to 2
2 | Sprint 1 | Portal, request types, queues, SLAs | ITSM Lead | 3 | 2 | 4 | 2026-01-19 | 2026-01-30 | bar: 3 to 4
3 | Sprint 2 | Confidential workflow, permissions, SSO | ITSM Lead | 5 | 2 | 6 | 2026-02-02 | 2026-02-13 | bar: 5 to 6
4 | Sprint 3 | Knowledge base v1, email-to-ticket, pilot prep | Product Owner | 7 | 2 | 8 | 2026-02-16 | 2026-02-27 | bar: 7 to 8
5 | Pilot | Pilot – Retail Operations & Finance | HR Ops Lead | 8 | 3 | 10 | 2026-02-23 | 2026-03-13 | bar: 8 to 10
6 | Sprint 4 | Pilot fixes, reporting dashboard | ITSM Lead | 9 | 2 | 10 | 2026-03-02 | 2026-03-13 | bar: 9 to 10
7 | Sprint 5 | Hardening, UAT, training, launch comms | PM | 11 | 2 | 12 | 2026-03-16 | 2026-03-27 | bar: 11 to 12
8 | Launch | Bank-wide launch | PM | 13 | 1 | 13 | 2026-03-30 | 2026-04-03 | bar: 13
9 | Hypercare | Hypercare & handover to IT support | ITSM Lead | 13 | 3 | 15 | 2026-03-30 | 2026-04-17 | bar: 13 to 15
10 | Milestone | Charter approved |  | 1 | 0 | 1 | 2026-01-05 | 2026-01-05 | bar: 1
11 | Milestone | Sprint 0 complete – backlog & design ready |  | 2 | 0 | 2 | 2026-01-12 | 2026-01-12 | bar: 2
12 | Milestone | Confidential workflow & SSO done (Sprint 2) |  | 6 | 0 | 6 | 2026-02-09 | 2026-02-09 | bar: 6
13 | Milestone | Pilot launch – 2 departments |  | 8 | 0 | 8 | 2026-02-23 | 2026-02-23 | bar: 8
14 | Milestone | UAT & readiness sign-off |  | 12 | 0 | 12 | 2026-03-23 | 2026-03-23 | bar: 12
15 | Milestone | Bank-wide launch |  | 13 | 0 | 13 | 2026-03-30 | 2026-03-30 | bar: 13
16 | Milestone | Hypercare exit & closure |  | 15 | 0 | 15 | 2026-04-13 | 2026-04-13 | bar: 15

## Stakeholders
Stakeholders
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Stakeholder | Role | Primary concern | Influence | Interest | Engagement approach
James Okoro | Executive Sponsor (CHRO) | Business outcome and timeline | High | High | Monthly checkpoint; sprint review demos
Joseph Mensah | Product Owner (HR Operations Manager) | Scope and user value | High | High | Daily availability; owns backlog priority
Kelechi Nwosu | Technology / Delivery Lead (IT Service Management Lead) | Feasibility and team capacity | High | High | Sprint planning; owns configuration & SSO
Mariam Bello | Operations Lead (HR Shared Services Supervisor) | Adoption and service continuity | Medium | High | Leads HR agent team; pilot coordinator
HR Business Partners | HR advisers (resistant group) | Losing personal relationship with 'their' employees | Medium | High | 1:1s; 'preferred adviser' field; involve in workflow design
Privacy & Compliance Officer | Compliance | Confidential case segregation, retention | High | Medium | Reviews permission design; sign-off before pilot
Information Security | IT Security | Access control, SSO | Medium | Low | Security review in Sprint 2
Employees (pilot departments) | Service users | Easy to ask, quick answers, privacy | Low | High | Pilot feedback survey; launch comms

## RACI
RACI
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Activity / deliverable | Sponsor | PM (Sola) | Product Owner | ITSM Lead | HR Ops Lead | Privacy Officer | Config Partner | A count (must be 1)
Charter & budget | A | R | C | C | I | I | I | 1
Backlog prioritisation | I | C | A | C | C | I | I | 1
Portal & queue configuration | I | C | C | A | C | I | R | 1
Confidential workflow & permissions | I | R | C | R | C | A | R | 1
Knowledge base content | I | C | A | I | R | I | I | 1
HR staff training & change management | I | A | C | I | R | I | C | 1
UAT sign-off | I | R | A | R | R | C | C | 1
Launch go / no-go | A | R | C | C | C | C | I | 1
Hypercare & handover to IT support | I | A | C | R | R | I | C | 1
R = Responsible · A = Accountable · C = Consulted · I = Informed. Check column: each row must have exactly one A.

## RAID Log
RAID Log
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Type | ID | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Response / action | Status | Review week
Risk | R-01 | HR Business Partners keep answering by email/WhatsApp, bypassing the queue | 4 | 4 | 16 | HR Ops Lead | Involve HRBPs in design; 'preferred adviser' routing; leadership message; retire WhatsApp | Open | 12
Risk | R-02 | Sensitive case logged in the general queue | 3 | 5 | 15 | Privacy Officer | Separate confidential request type; restricted project; permission tests | Occurred → I-01 | 9
Risk | R-03 | SSO integration delayed by Identity team | 3 | 4 | 12 | ITSM Lead | Agreed slot in Sprint 2; fallback: local accounts for pilot only | Closed | 6
Risk | R-04 | Knowledge articles not ready for launch | 3 | 3 | 9 | Product Owner | Article owners assigned per topic; weekly tracker | Open | 10
Assumption | A-01 | Existing Jira Service Management licence covers HR agents |  |  |  | ITSM Lead | Validated – 12 extra agent licences purchased | Validated | 2
Issue | I-01 | Pilot week 1: a grievance was logged as a 'General question' and was visible to 6 HR agents | 5 | 5 | 25 | PM | Contained same day; workflow change – see decision log D-04 | Resolved | 9
Dependency | D-01 | Identity team SSO configuration |  |  |  | ITSM Lead | Delivered Week 6 | Closed | 6
Dependency | D-02 | HR content owners for 40 knowledge articles |  |  |  | Product Owner | 38 of 40 ready by Week 12; 2 published in hypercare | Closed | 12
Open risks scored 15+: |  | 1

## Comms Plan
Comms Plan
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Audience | Information | Format / channel | Frequency | Owner | Escalation route
Sponsor & checkpoint group | Progress, burn-up, risks, decisions | Monthly checkpoint + 1-page update | Monthly / weekly email | PM | Sponsor
Scrum team | Sprint goal, blockers | Daily stand-up (15 min), sprint planning, retro | Daily / bi-weekly | PM | Product Owner
Stakeholders | Working software | Sprint review demo | Every 2 weeks | Product Owner | PM
HR agents & HRBPs | Process changes, training, 'what's in it for me' | Team sessions, 1:1s, user guide | Weekly during pilot/launch | HR Ops Lead | PM
All employees | How to get HR help, privacy assurance | Intranet article, email from CHRO, posters | Pilot launch + bank-wide launch | Product Owner | Sponsor
Privacy & Compliance | Permission design, incidents | Review meeting; immediate notice for incidents | Per sprint / same day | PM | Sponsor

## Budget
Budget
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Cost category | Amount (CAD) | Notes
Configuration partner (Jira Service Management) | 62000 | Fixed price
Additional agent licences (Year 1) | 24000 | HR agents
Internal IT (SSO, directory integration) | 28000
Knowledge-base content & training | 22000 | Writer + HR SMEs
Project management / Scrum facilitation | 27600
Contingency (10%) | 16400
Total | 180000
Contingency as % of total | 9.111%

## Product Backlog
Product Backlog
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
ID | Epic | User story | Priority | Story points | Acceptance criteria | Sprint | Status
HR-01 | Portal | As an employee, I can raise an HR request from one portal so I don't need to know who to email | Must | 5 | Portal reachable via SSO; 12 request types; confirmation email sent | 1 | Done
HR-02 | Queues & SLAs | As an HR agent, I see a shared queue sorted by SLA so nothing is missed | Must | 5 | Queue by request type; SLA timer 1 business day for first response | 1 | Done
HR-03 | Confidential | As an employee, I can raise a confidential concern that only investigators can see | Must | 8 | Separate restricted project; only 'HR Investigator' role can view; tested with 5 non-authorised roles | 2 | Done
HR-04 | Identity | As an employee, I sign in with my bank account (SSO) and my details auto-fill | Must | 5 | SSO works for 100% of test users; department and manager auto-populated | 2 | Done
HR-05 | Knowledge | As an employee, I see suggested articles before submitting | Should | 3 | Top 3 articles suggested from keywords | 3 | Done
HR-06 | Channels | As an employee, I can email hr@ and a ticket is created | Must | 3 | Email creates ticket in under 2 min; reply threads stay on the ticket | 3 | Done
HR-07 | Routing | As an HRBP, tickets from 'my' departments are routed to me first | Should | 5 | 'Preferred adviser' field routes by department; falls back to queue after 4 h | 4 | Done
HR-08 | Confidential | System warns and re-routes when a general ticket contains sensitive keywords | Must (added via D-04) | 5 | Keywords (e.g., grievance, harassment) trigger restricted re-route + Privacy Officer alert | 4 | Done
HR-09 | Reporting | As HR leadership, I see volume, SLA and top themes monthly | Should | 5 | Dashboard with 4 charts; data matches queue export | 4 | Done
HR-10 | Feedback | As an employee, I rate my experience when a ticket closes | Could | 2 | 1–5 rating; 1-click | 5 | Done
HR-11 | Chatbot | Virtual agent answers common questions | Won't (this release) | 13 | — | Future | Deferred