## Start Here
Construction Cost Control Recovery – PM Workbook
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Organisation | Lakeline Developments (fictional) – mid-sized property company; 6-storey, 96-unit residential building in Edmonton, AB
Sponsor | Fatima Sule, Development Director
Project Manager | Sola Debanjo, PMP
Approach | Hybrid (Waterfall construction schedule + 2-week Agile sprints to build cost controls)
Duration (weeks) | 51
Budget (assumed) | CAD $650,000 for the recovery programme (assumed); controls a $38M construction budget
How to use this workbook
• Blue text on a yellow background = an input you can change (e.g., project start date, status week, actuals).
• Black text = formulas. They recalculate automatically when inputs change.
• Gantt: change the project start date or a task's start week/duration and the bars and dates move.
• RAID: Score = Probability × Impact; colour turns red at 15+, amber at 8–14.
• The schedule is also provided as a Microsoft Project XML file (opens in MS Project or the free ProjectLibre).

## EVM Dashboard
Construction Cost Control Recovery – earned value (remaining scope)
Simulated data – built in Excel
Budget at completion – remaining scope (BAC) | 22800000 | Week | PV ($M) | EV ($M) | AC ($M)
Spent before recovery started | 15200000 | 0 | 0
Original total budget | 38000000 | 2 | 0
Status week | 26 | 4 | 0 | 0 | 0
|  | 6 | 0.12 | 0.12 | 0.12
Planned Value (PV) | 11400000 | 8 | 0.46 | 0.46 | 0.49
Earned Value (EV) | 10900000 | 10 | 1.03 | 1.02 | 1.08
Actual Cost (AC) | 11200000 | 12 | 1.81 | 1.78 | 1.88
Cost Variance (CV = EV − AC) | -300000 | 14 | 2.78 | 2.73 | 2.87
Schedule Variance (SV = EV − PV) | -500000 | 16 | 3.93 | 3.84 | 4.03
CPI (EV ÷ AC) | 0.97321 | 18 | 5.24 | 5.09 | 5.32
SPI (EV ÷ PV) | 0.95614 | 20 | 6.66 | 6.45 | 6.71
EAC – remaining scope (BAC ÷ CPI) | 23427522.9358 | 22 | 8.19 | 7.89 | 8.18
Forecast final cost | 38627522.9358 | 24 | 9.78 | 9.39 | 9.69
Variance vs original budget | 1.651% | 26 | 11.4 | 10.9 | 11.2
|  | 28 | 13.02
Target: CPI ≥ 0.97 by Month 6; forecast final cost within +3% of original budget. |  | 30 | 14.61
CPI target met? | Yes | 32 | 16.14
Cost target met? | Yes | 34 | 17.56
|  | 36 | 18.87
|  | 38 | 20.02
|  | 40 | 20.99
|  | 42 | 21.77
|  | 44 | 22.34
|  | 46 | 22.68
|  | 48 | 22.8
|  | 50 | 22.8

## Gantt
Gantt Schedule
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
| Start date (Week 1): | 2026-05-11
ID | Phase | Work package / milestone | Owner | Start wk | Duration (wks) | End wk | Start date | Finish date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | Recovery Initiation | Recovery charter & governance | PM | 1 | 2 | 2 | 2026-05-11 | 2026-05-22 | bar: 1 to 2
2 | Recovery Initiation | Cost audit & re-baseline (cost-to-complete) | Cost Consultant | 2 | 3 | 4 | 2026-05-18 | 2026-06-05 | bar: 2 to 4
3 | Cost Controls (Agile sprints) | Sprint 1–2 – committed-cost register, change-order process | Commercial Mgr | 3 | 4 | 6 | 2026-05-25 | 2026-06-19 | bar: 3 to 6
4 | Cost Controls (Agile sprints) | Sprint 3–4 – invoice verification, EVM report | PM | 7 | 4 | 10 | 2026-06-22 | 2026-07-17 | bar: 7 to 10
5 | Construction | Structure (floors 3–6) & roof | General Contractor | 5 | 10 | 14 | 2026-06-08 | 2026-08-14 | bar: 5 to 14
6 | Construction | Building envelope – windows, cladding, roofing | General Contractor | 13 | 12 | 24 | 2026-08-03 | 2026-10-23 | bar: 13 to 24
7 | Construction | Mechanical, electrical, plumbing rough-in | General Contractor | 20 | 16 | 35 | 2026-09-21 | 2027-01-08 | bar: 20 to 35
8 | Construction | Interior finishes | General Contractor | 34 | 12 | 45 | 2026-12-28 | 2027-03-19 | bar: 34 to 45
9 | Construction | Elevators & life-safety systems | General Contractor | 36 | 9 | 44 | 2027-01-11 | 2027-03-12 | bar: 36 to 44
10 | Commissioning & Handover | Commissioning & testing | Construction Mgr | 44 | 4 | 47 | 2027-03-08 | 2027-04-02 | bar: 44 to 47
11 | Commissioning & Handover | Occupancy inspection & permit | Construction Mgr | 47 | 3 | 49 | 2027-03-29 | 2027-04-16 | bar: 47 to 49
12 | Commissioning & Handover | Snagging, O&M manuals, handover | Ops Lead | 48 | 4 | 51 | 2027-04-05 | 2027-04-30 | bar: 48 to 51
13 | Commissioning & Handover | Closure report & lessons learned | PM | 50 | 2 | 51 | 2027-04-19 | 2027-04-30 | bar: 50 to 51
14 | Milestone | Recovery charter approved |  | 2 | 0 | 2 | 2026-05-18 | 2026-05-18 | bar: 2
15 | Milestone | Cost audit & re-baseline approved |  | 4 | 0 | 4 | 2026-06-01 | 2026-06-01 | bar: 4
16 | Milestone | Cost controls live (change orders, invoice checks) |  | 8 | 0 | 8 | 2026-06-29 | 2026-06-29 | bar: 8
17 | Milestone | Structure topped out |  | 14 | 0 | 14 | 2026-08-10 | 2026-08-10 | bar: 14
18 | Milestone | Building envelope closed (before winter) |  | 24 | 0 | 24 | 2026-10-19 | 2026-10-19 | bar: 24
19 | Milestone | MEP rough-in & pre-drywall inspection passed |  | 36 | 0 | 36 | 2027-01-11 | 2027-01-11 | bar: 36
20 | Milestone | Construction substantially complete |  | 46 | 0 | 46 | 2027-03-22 | 2027-03-22 | bar: 46
21 | Milestone | Occupancy permit |  | 49 | 0 | 49 | 2027-04-12 | 2027-04-12 | bar: 49
22 | Milestone | Handover & closure |  | 51 | 0 | 51 | 2027-04-26 | 2027-04-26 | bar: 51

## Stakeholders
Stakeholders
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Stakeholder | Role | Primary concern | Influence | Interest | Engagement approach
Fatima Sule | Project Sponsor (Development Director) | Schedule, cost and business outcome | High | High | Bi-weekly control board; monthly EVM report; decision memos
Michael Adekunle | Technical / Site Lead (Construction Manager) | Feasibility, sequencing and quality | High | High | Daily site check-ins; weekly look-ahead; owns site verification
Grace Nnamdi | Commercial / Procurement Lead (Commercial Manager) | Supplier performance and cost control | High | High | Weekly cost meeting; owns commitments and change orders
Femi Balogun | Operations / End User Lead (Property Operations Manager) | Continuity, safety and acceptance | Medium | Medium | Monthly; leads handover acceptance and O&M manuals
General Contractor PM | Main contractor | Payment, schedule, change approvals | High | High | Weekly progress meeting; invoice verification walk
Cost consultant (QS) | Advisor | Accurate valuation | Medium | High | Weekly; values progress and change orders
Lender's monitor | Financier | Budget covenant, drawdowns | High | Medium | Monthly EVM report; site visit quarterly
City building inspector | Regulator | Code compliance, permits | High | Low | Inspection booking 2 weeks ahead; pre-inspections
Window / curtain-wall supplier | Key supplier | Production schedule, payment | Medium | Medium | Bi-weekly production updates; factory evidence

## RACI
RACI
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Activity / deliverable | Sponsor | PM (Sola) | Construction Mgr | Commercial Mgr | General Contractor | Cost Consultant | Ops Lead | A count (must be 1)
Recovery charter & re-baseline | A | R | C | C | C | R | I | 1
Committed-cost register | I | A | C | R | C | C | I | 1
Change-order assessment & approval | A | R | C | R | C | R | I | 1
Invoice-to-progress verification | I | A | R | C | C | R | I | 1
Monthly EVM & lender report | I | A | C | C | I | R | I | 1
Site execution & sequencing | I | C | A | I | R | I | I | 1
Quality inspections | I | C | A | I | R | I | C | 1
Handover & snagging acceptance | A | R | R | I | R | I | R | 1
R = Responsible · A = Accountable · C = Consulted · I = Informed. Check column: each row must have exactly one A.

## RAID Log
RAID Log
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Type | ID | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Response / action | Status | Review week
Risk | R-01 | Window supplier misses delivery, so the envelope is not closed before winter | 3 | 5 | 15 | Commercial Mgr | Factory production evidence every 2 weeks; temporary enclosure plan ready | Occurred → I-02 | 20
Risk | R-02 | Contractor resists invoice verification, slowing payments and goodwill | 3 | 3 | 9 | PM | Joint verification walk on fixed day; pay within 15 days of verified claim | Closed | 10
Risk | R-03 | Hidden unapproved change orders appear in final accounts | 4 | 4 | 16 | Commercial Mgr | Amnesty: all pending verbal changes submitted by Week 6; none accepted after | Open | 8
Risk | R-04 | City inspection booking delays | 3 | 3 | 9 | Construction Mgr | Book 2 weeks ahead; contractor pre-inspection checklist | Open | 34
Risk | R-05 | Material price increase on remaining packages | 2 | 4 | 8 | Commercial Mgr | Lock prices on remaining commitments at re-baseline | Closed | 6
Assumption | A-01 | No major design changes after re-baseline |  |  |  | Sponsor | Design freeze agreed at Week 4 | Validated | 4
Issue | I-01 | Cost audit found $1.1M of verbal change orders with no paperwork | 5 | 4 | 20 | Commercial Mgr | Each priced by cost consultant; 31% rejected or reduced | Resolved | 8
Issue | I-02 | Window supplier missed delivery milestone (Week 18); claimed '2 weeks late' | 5 | 5 | 25 | PM | Decision D-04 – see decision log | Resolved | 24
Dependency | D-01 | City building inspections at hold points |  |  |  | Construction Mgr | Inspection calendar shared with contractor | Open | 36
Dependency | D-02 | Utility permanent power connection before commissioning |  |  |  | Construction Mgr | Application submitted Week 10 | Open | 40
Dependency | D-03 | Window supplier production slot |  |  |  | Commercial Mgr | Tracked via bi-weekly factory evidence | Open | 20
Open risks scored 15+: |  | 1

## Comms Plan
Comms Plan
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Audience | Information | Format / channel | Frequency | Owner | Escalation route
Project Control Board | Cost, EVM, change orders, decisions | Meeting + control pack | Every 2 weeks | PM | Sponsor
Sponsor | Status, top risks, decisions | 1-page update | Weekly | PM | Control Board
Lender's monitor | EVM, forecast final cost, schedule | Monthly EVM report | Monthly | PM | Sponsor
General contractor | Progress, look-ahead, invoice verification | Site progress meeting + verification walk | Weekly | Construction Mgr | PM
Suppliers | Production and delivery status | Supplier call + evidence (photos, shipping docs) | Bi-weekly | Commercial Mgr | PM
Property operations | Handover readiness, O&M, training | Handover meeting | Monthly; weekly from Week 44 | PM | Sponsor

## Budget
Budget
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Cost category | Amount (CAD) | Notes
Recovery PM & project controls | 240000 | PM, cost controller
Cost consultant / quantity surveyor | 180000 | 3 days/week
Cost-control software & reporting setup | 45000
Independent inspections & testing | 95000 | Envelope water test, fire-stopping review
Contingency (recovery programme) | 90000
Total | 650000
Contingency as % of total | 13.85%

## Contractor Tracker
Procurement / Contractor Tracker (status at Week 20)
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Package | Supplier / subcontractor (fictional) | Contract value | Approved changes | Revised value | Site-verified % complete | Verified value earned | Invoiced to date | Over-claimed (invoiced − verified) | Required on site | Forecast | Status | Inspection / acceptance
Structural framing | Northline Framing Ltd. | 4200000 | 85000 | 4285000 | 86% | 3612000 | 3610000 | 0 | Week 5 | On site | Green | Framing inspection – passed
Windows & curtain wall | ClearSpan Glazing Inc. | 2650000 | 0 | 2650000 | 30% | 795000 | 795000 | 0 | Week 16 | Week 21 (was Week 16) | Red → Amber | Water test per floor
Roofing | Summit Roof Systems | 780000 | 22000 | 802000 | 92% | 717600 | 710000 | 0 | Week 15 | Complete | Green | Roof inspection – passed
Mechanical & plumbing | Prairie Mechanical Ltd. | 5100000 | 140000 | 5240000 | 29% | 1479000 | 1479000 | 0 | Week 20 | On site | Green | Pre-drywall inspection
Electrical | Bright Circuit Electric | 3900000 | 65000 | 3965000 | 28% | 1092000 | 1092000 | 0 | Week 20 | On site | Green | Pre-drywall inspection
Elevators | Vertex Lifts Canada | 620000 | 0 | 620000 | 15% | 93000 | 93000 | 0 | Week 36 | Week 36 | Green | Elevator safety inspection
Drywall & interiors | Capital Interiors Inc. | 2300000 | 0 | 2300000 | 0% | 0 | 0 | 0 | Week 34 | Week 34 | Green | Snagging per unit
Flooring & finishes | River Valley Finishes | 1450000 | 0 | 1450000 | 0% | 0 | 0 | 0 | Week 38 | Week 38 | Green | Snagging per unit
Total |  | 21000000 | 312000 | 21312000 |  | 7788600 | 7779000 | 0