## Start Here
Project Portfolio Dashboard – PM Workbook
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Organisation | Meridian Advisory (fictional) – professional services firm with 6 practices and ~40 active client projects
Sponsor | Michael Adekunle, Managing Partner
Project Manager | Sola Debanjo, PMP
Approach | Hybrid (Waterfall for data & governance, Agile sprints for dashboard build)
Duration (weeks) | 18
Budget (assumed) | CAD $150,000 (assumed; includes 10% contingency)
How to use this workbook
• Blue text on a yellow background = an input you can change (e.g., project start date, status week, actuals).
• Black text = formulas. They recalculate automatically when inputs change.
• Gantt: change the project start date or a task's start week/duration and the bars and dates move.
• RAID: Score = Probability × Impact; colour turns red at 15+, amber at 8–14.
• The schedule is also provided as a Microsoft Project XML file (opens in MS Project or the free ProjectLibre).

## Dashboard
Meridian Advisory – Portfolio overview
Simulated data – built in Excel
Active projects |  | Red |  | Amber | Green | Total budget | Spent to date
12 |  | 2 |  | 4 | 6 | 4040 | 2311
Project | Schedule variance (days) | Cost index | Overall RAG
MA-101 | -3 | 1.0375 | Green
MA-102 | -18 | 0.77758 | Red
MA-103 | 0 | 0.97826 | Green
MA-104 | -9 | 0.90466 | Amber
MA-105 | 2 | 1.0488 | Green
MA-106 | -6 | 0.89674 | Amber
MA-107 | -2 | 0.988 | Green
MA-108 | -12 | 0.7474 | Red
MA-109 | -4 | 1.0322 | Amber
MA-110 | 1 | 1.0586 | Green
MA-111 | -1 | 1.0369 | Green
MA-112 | -8 | 0.89571 | Amber

## Gantt
Gantt Schedule
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
| Start date (Week 1): | 2026-01-05
ID | Phase | Work package / milestone | Owner | Start wk | Duration (wks) | End wk | Start date | Finish date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | Initiation | Charter & stakeholder interviews | PM | 1 | 2 | 2 | 2026-01-05 | 2026-01-16 | bar: 1 to 2
2 | Analysis & Design | Current-state review (6 practices) | Head of PMO | 2 | 3 | 4 | 2026-01-12 | 2026-01-30 | bar: 2 to 4
3 | Analysis & Design | Data dictionary, RAG rules, future process | Head of PMO | 4 | 3 | 6 | 2026-01-26 | 2026-02-13 | bar: 4 to 6
4 | Data | Finance & resourcing data feeds | BI Lead | 6 | 4 | 9 | 2026-02-09 | 2026-03-06 | bar: 6 to 9
5 | Build Sprints | Sprint 1 – status template & pilot practice | Delivery Ops | 7 | 2 | 8 | 2026-02-16 | 2026-02-27 | bar: 7 to 8
6 | Build Sprints | Sprint 2 – data model & portfolio overview page | BI Lead | 9 | 2 | 10 | 2026-03-02 | 2026-03-13 | bar: 9 to 10
7 | Build Sprints | Sprint 3 – financials & risk pages | BI Lead | 11 | 2 | 12 | 2026-03-16 | 2026-03-27 | bar: 11 to 12
8 | Build Sprints | Sprint 4 – resourcing page, security, hardening | BI Lead | 13 | 2 | 14 | 2026-03-30 | 2026-04-10 | bar: 13 to 14
9 | Rollout | Training & rollout to all practices | Delivery Ops | 10 | 5 | 14 | 2026-03-09 | 2026-04-10 | bar: 10 to 14
10 | Rollout | Go-live for annual planning | PM | 16 | 1 | 16 | 2026-04-20 | 2026-04-24 | bar: 16
11 | Closure | Benefits check & closure report | PM | 17 | 2 | 18 | 2026-04-27 | 2026-05-08 | bar: 17 to 18
12 | Milestone | Charter approved |  | 1 | 0 | 1 | 2026-01-05 | 2026-01-05 | bar: 1
13 | Milestone | Current state & requirements signed off |  | 4 | 0 | 4 | 2026-01-26 | 2026-01-26 | bar: 4
14 | Milestone | Data dictionary & RAG rules approved |  | 6 | 0 | 6 | 2026-02-09 | 2026-02-09 | bar: 6
15 | Milestone | Status template live (pilot practice) |  | 8 | 0 | 8 | 2026-02-23 | 2026-02-23 | bar: 8
16 | Milestone | Dashboard v1 – sprint review |  | 12 | 0 | 12 | 2026-03-23 | 2026-03-23 | bar: 12
17 | Milestone | All practices reporting |  | 14 | 0 | 14 | 2026-04-06 | 2026-04-06 | bar: 14
18 | Milestone | Dashboard live for annual planning |  | 16 | 0 | 16 | 2026-04-20 | 2026-04-20 | bar: 16
19 | Milestone | Benefits check & closure |  | 18 | 0 | 18 | 2026-05-04 | 2026-05-04 | bar: 18

## Stakeholders
Stakeholders
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Stakeholder | Role | Primary concern | Influence | Interest | Engagement approach
Michael Adekunle | Executive Sponsor (Managing Partner) | Business outcome and timeline | High | High | Bi-weekly steering; dashboard previews
Grace Nnamdi | Product / Business Owner (Head of PMO) | Scope and user value | High | High | Weekly; owns RAG rules and template
Femi Balogun | Technology / Delivery Lead (BI Lead) | Feasibility and team capacity | Medium | High | Sprint planning; owns data model
Halima Garba | Operations / Customer Lead (Delivery Operations Manager) | Adoption and service continuity | Medium | High | Weekly; owns rollout & training
Practice Leads (6) | Senior partners | Fair view of their practice; extra features | High | Medium | Monthly demos; consulted on views
Project Managers (35) | Data providers / users | Less admin, not more | Low | High | Champions, 30-min training, feedback form
Head of Finance | Data owner (budget/actuals) | Accuracy, confidentiality | High | Medium | Data-sharing agreement; reconciliation sign-off
IT Security | Access control | Who sees what | Medium | Low | Row-level security review

## RACI
RACI
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Activity / deliverable | Sponsor | PM (Sola) | Head of PMO | BI Lead | Delivery Ops | Finance | Practice Leads | A count (must be 1)
Charter | A | R | C | C | I | I | I | 1
Current/future-state process | I | A | R | C | R | I | C | 1
RAG rules & data dictionary | I | R | A | C | C | C | C | 1
Data model & finance feed | I | C | C | A | I | R | I | 1
Dashboard build (sprints) | I | C | C | A | I | I | C | 1
Training & adoption | I | C | C | I | A | I | I | 1
Change requests | A | R | C | C | I | I | C | 1
Benefits tracking | I | A | R | C | C | I | I | 1
R = Responsible · A = Accountable · C = Consulted · I = Informed. Check column: each row must have exactly one A.

## RAID Log
RAID Log
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Type | ID | Description | Probability (1-5) | Impact (1-5) | Score | Owner | Response / action | Status | Review week
Risk | R-01 | PMs see the template as extra admin and don't submit on time | 4 | 4 | 16 | Delivery Ops | Template takes under 15 min; pre-filled finance data; champions; compliance shown on dashboard | Open | 14
Risk | R-02 | Practice leads dispute their RAG ratings | 3 | 4 | 12 | Head of PMO | RAG rules agreed by all practice leads at Week 6; rule-based, not opinion | Closed | 6
Risk | R-03 | Finance data doesn't reconcile with project budgets | 3 | 4 | 12 | BI Lead | Reconciliation check each refresh; Finance sign-off | Open | 12
Risk | R-04 | Late scope requests from senior partners threaten fixed date | 4 | 3 | 12 | PM | Change control; Phase 2 backlog | Occurred → I-01 | 12
Assumption | A-01 | Power BI licences available for all leaders |  |  |  | BI Lead | Validated; 12 Pro licences added | Validated | 3
Issue | I-01 | Practice lead requested consultant-level utilisation view at Week 12 | 5 | 3 | 15 | PM | CR-02 assessed and deferred to Phase 2 (D-04) | Resolved | 12
Dependency | D-01 | Weekly finance export (budget vs actual) |  |  |  | Finance | Live Week 9 | Closed | 9
Open risks scored 15+: |  | 1

## Comms Plan
Comms Plan
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Audience | Information | Format / channel | Frequency | Owner | Escalation route
Steering group | Progress, decisions, risks | Meeting + 1-page status | Every 2 weeks | PM | Sponsor
Practice champions | Working dashboard, feedback | Sprint review demo | Every 2 weeks | BI Lead | PM
Project managers | New template, deadlines, how-to | 30-min training, Teams channel, quick guide | Weekly during rollout | Delivery Ops | Head of PMO
Practice leads | Practice view, RAG rules | Monthly demo | Monthly | Head of PMO | Sponsor
All staff | Why we're changing | Managing Partner note | Once at launch | Sponsor | —

## Budget
Budget
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Cost category | Amount (CAD) | Notes
BI developer (contract, 14 weeks) | 64000
Data engineering (finance & resourcing feeds) | 28000
Change management & training | 18000 | Includes PM time
Project management | 26000
Contingency (10%) | 14000
Total | 150000
Contingency as % of total | 9.333%

## Portfolio Data
Portfolio data with rule-based RAG (formulas)
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Project ID | Practice | Client sector | Budget (CAD) | Actual to date (CAD) | % complete | Schedule variance (days) | Open high risks | Staffing gap (FTE) | Cost index | Schedule RAG | Cost RAG | Risk RAG | Staffing RAG | Overall RAG
MA-101 | Digital | Healthcare | 420000 | 251000 | 62% | -3 | 1 | 0 | 1.0375 | Green | Green | Green | Green | Green
MA-102 | Digital | Telecom | 610000 | 455000 | 58% | -18 | 3 | 1 | 0.77758 | Red | Red | Red | Red | Red
MA-103 | Finance Advisory | Public sector | 180000 | 92000 | 50% | 0 | 0 | 0 | 0.97826 | Green | Green | Green | Green | Green
MA-104 | Operations | Construction | 350000 | 236000 | 61% | -9 | 2 | 0.5 | 0.90466 | Amber | Amber | Amber | Amber | Amber
MA-105 | Operations | Manufacturing | 270000 | 121000 | 47% | 2 | 0 | 0 | 1.0488 | Green | Green | Green | Green | Green
MA-106 | People & Change | Healthcare | 150000 | 92000 | 55% | -6 | 1 | 0.5 | 0.89674 | Amber | Amber | Green | Amber | Amber
MA-107 | Risk | Financial services | 520000 | 200000 | 38% | -2 | 1 | 0 | 0.988 | Green | Green | Green | Green | Green
MA-108 | Digital | Retail | 300000 | 289000 | 72% | -12 | 2 | 0 | 0.7474 | Amber | Red | Amber | Green | Red
MA-109 | Data & AI | Telecom | 460000 | 205000 | 46% | -4 | 1 | 0.5 | 1.0322 | Green | Green | Green | Amber | Amber
MA-110 | Data & AI | Energy | 380000 | 140000 | 39% | 1 | 0 | 0 | 1.0586 | Green | Green | Green | Green | Green
MA-111 | Finance Advisory | Construction | 210000 | 160000 | 79% | -1 | 0 | 0 | 1.0369 | Green | Green | Green | Green | Green
MA-112 | People & Change | Public sector | 190000 | 70000 | 33% | -8 | 1 | 0 | 0.89571 | Amber | Amber | Green | Green | Amber

## RAG Rules
RAG rules (agreed by all practice leads, Week 6)
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
Dimension | Green | Amber | Red
Schedule variance (days) | 0 to −5 | −6 to −15 | worse than −15
Cost index | ≥ 0.95 | 0.85–0.94 | < 0.85
Open high risks | 0–1 | 2 | 3 or more
Staffing gap (FTE) | 0 | 0.5 | 1 or more
Overall RAG = the worst of the four dimensions (calculated in 'Portfolio Data', column O).

## Benefits KPIs
Benefits KPIs
Simulated project – organisation, people and figures are fictional (PM Project Lab practice brief).
KPI | Baseline (simulated) | Target | Week 16 (simulated) | Measurement | Owner
Projects reporting via standard template | 0% | 100% | 100% (40/40) | Submissions ÷ active projects | Delivery Ops
PM time to prepare weekly report | ~3 h | ≤ 1 h | 50 min (survey, n=31) | PM pulse survey | Head of PMO
Required fields complete & on time | n/a | ≥ 95% | 96% | Data-quality check each refresh | BI Lead
Portfolio meeting uses dashboard as agenda | No | Yes | Yes from Week 16 | Meeting minutes | Sponsor